## Timeline
Cutover Draft / Friday, 25 June 2021
|  |  | Dryer 1 System |  |  | Dryer 2 System |  |  | Dryer 3 System |  |  | Wet Mix Systems
|  | Lactose | Dryer 1 |  | Standardiser 1 | Dryer 2 |  | Standardiser 2 | Dryer 3 |  | Standardiser 3 | Separators | Cream Pasterisers | AMF | Lactoferin | RPD | DLP1 | PD1 | OT Timeline | TPM Window
Tue 30 Nov | 15:00
| 16:00 | [14 empty] | Run until 1700
| 17:00 | [14 empty] | OFF AT 1700
| 18:00 | [14 empty] | Planned OFF
| 19:00 | [14 empty] | Planned OFF
| 20:00 | Run until 2100 |  |  | Run until 2100 |  |  | Run until 2100 | [5 empty] | Run until 2100 | Run until 2100 | Planned OFF
| 21:00 | OFF AT 2100 |  |  | OFF AT 2100 |  |  | OFF AT 2100 | [5 empty] | OFF AT 2100 | OFF AT 2100 | Planned OFF |  |  |  | TPM Window
| 22:00 | Planned OFF |  |  | Planned OFF |  |  | Planned OFF |  |  | Run until 2300 |  |  | Planned OFF | Planned OFF | Planned OFF
| 23:00 | Planned OFF | Run until 0000 |  | Planned OFF |  |  | Planned OFF |  |  | OFF AT 2300 | Run until 0000 | Run until 0000 | Planned OFF | Planned OFF | Planned OFF
Wed 01 Dec | 24:00 | Planned OFF | OFF AT 0000 |  | Planned OFF |  |  | Planned OFF |  |  | Planned OFF | OFF AT 0000 | OFF AT 0000 | Planned OFF | Planned OFF | Planned OFF
| 25:00 | Planned OFF | Planned OFF |  | Planned OFF |  |  | Planned OFF |  |  | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF
| 26:00 | Planned OFF | Planned OFF |  | Planned OFF |  |  | Planned OFF |  |  | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF
| 27:00 | Planned OFF | Planned OFF |  | Planned OFF |  |  | Planned OFF |  |  | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF
| 28:00 | Planned OFF | Planned OFF |  | Planned OFF |  |  | Planned OFF |  |  | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF | Planned OFF
| 29:00 | Planned OFF | OFF UNTIL 0600 |  | Planned OFF | Run until 0600 |  | OFF UNTIL 0600 |  |  | OFF UNTIL 0600 | OFF UNTIL 0600 | OFF UNTIL 0600 | Planned OFF | Planned OFF | Planned OFF
| 30:00 | OFF UNTIL 0700 | Anticipated Restart 0600 | Packer | Planned OFF | OFF AT 0600 |  | Anticipated Restart 0600 | Run until 0700 |  | Anticipated Restart 0600 | Anticipated Restart 0600 | Anticipated Restart 0600 | Planned OFF | Planned OFF | Planned OFF
| 31:00 | Anticipated Restart 0700 |  | Packer | Planned OFF | Planned OFF |  |  | OFF AT 0700 |  |  |  |  | Planned OFF | Planned OFF | Planned OFF
| 32:00 |  |  |  | Planned OFF | Planned OFF | Packer |  | Planned OFF |  |  |  |  | OFF UNTIL 0900 | OFF UNTIL 0900 | OFF UNTIL 0900
| 33:00 |  |  |  | Planned OFF | OFF UNTIL 1000 | Packer |  | Planned OFF |  |  |  |  | Anticipated Restart 0900 | Anticipated Restart 0900 | Anticipated Restart 0900
| 34:00 |  |  |  | Planned OFF | Anticipated Restart 1000 |  |  | OFF UNTIL 1100 | Packer
| 35:00 |  |  |  | Planned OFF |  |  |  | Anticipated Restart 1100 | Packer
| 36:00 |  |  |  | Planned OFF
| 37:00 |  |  |  | Planned OFF
| 38:00 |  |  |  | Planned OFF
| 39:00 |  |  |  | OFF UNTIL 1600
| 40:00 |  |  |  | Anticipated Restart 1600
Note on F11: Mat Chavez: Known shutoff requirements?

## Notes
Notes from meeting 22 Jun Mat & Rob A
#Need to carry Lactose over in Silo's
#RPD is day-shift only, and they will be off.
#DLP1 needs to be handled because #FSSI needs to be "delayed". @Paul-Doney to talk to "Glenn" at #FSSI. See @Michael-Hawke about #DLP1 Planning
#Pokeno has sold milk to 'neighbour' from 1 Dec
#Pokeno running day shift on 30 Nov as long as @Rob-Allfrey is able to sell milk to "neighbours"
Notes from meeting 25 Jun, Mat & Dominique
TPM for Dunsandel is a single database
TPM is not required immediately for D123 restart
D123 should be prepped to restart manually first go to ensure low risk of "too much milk"
Wetmix MUST have TPM running to restart
Packer changes have risk; one trained human right now